## Tasks
| Task | Status
1 | Segregate Pred and Training code | Done
2 | Send screenshots of folder structures | Done
3 | Check in code in Devops Repo | Done
4 | Move All datasets into Sql Tables | Done
5 | Make file names standard and in snakecase | Done
6 | Get model matrix and feature importance in an excel | Done
7 | Prepare a message for all the contributors of VLP | Done
8 | Run model training with driver json
9 | Get model results for train, validation and test | Done
10 | Writing a document for these requirements
11 | Naming conventions for batch endpoints
12 | Screenshot of the API on swagger
13 | State over model or configuration driven feature list to make Api robust (features required for prediction will come with model in pickle file and then will extract that features from the Json)
14 | Middleware (Research middleware and replace Api script with middleware)
15 | Logging (Think about how to do the logs and Api hits and how to store them e.g. store in a database)
16 | Authorization (think about what type of authorization should be there in this Api)
17 | Flask vs restapi and Pydantic models (diff b/w flask and restapi and what are pydantic models)
18 | Create different excel for different model containing the feature importance and confusion matrix for each.
19 | Also mention date and time when each of these updates were made